# Application Rationalization Project Plan

## Client Engagement Template

## Executive Summary

This project plan outlines a comprehensive approach to evaluate, analyze, and rationalize a client's application portfolio. The engagement will identify opportunities for cost reduction, risk mitigation, and strategic alignment while providing a clear roadmap for portfolio optimization.

Typical Duration: 8-12 weeks (depending on portfolio size)

Key Deliverables: Portfolio assessment, stakeholder insights, rationalization recommendations, implementation roadmap

## Phase 1: Project Initiation & Discovery

### Duration: Week 1-2

### Objectives

Establish project governance and communication protocols

Understand client's strategic objectives and constraints

Define scope, success criteria, and key stakeholders

Set up project infrastructure and tools

### Activities

| Activity | Owner | Duration | Deliverable |
| --- | --- | --- | --- |
| Kick-off meeting with executive sponsor | Project Lead | Day 1 | Meeting notes, project charter |
| Identify key stakeholders and interview candidates | Project Lead | Days 1-3 | Stakeholder registry |
| Review existing documentation (architecture diagrams, contracts, etc.) | Analyst | Days 2-5 | Documentation inventory |
| Define assessment criteria and weighting with client | Project Lead | Days 3-5 | Scoring criteria document |
| Configure Application Rationalization Tool | Technical Lead | Days 4-7 | Configured tool instance |
| Establish data collection templates | Analyst | Days 5-7 | Data templates |
| Communication plan and status reporting cadence | Project Lead | Day 7 | Communication plan |

### Key Meetings

**Kick-off Meeting**: Align on objectives, scope, timeline

**Stakeholder Identification Workshop**: Map stakeholders to applications

**Criteria Definition Workshop**: Customize scoring weights for client context

### Deliverables

Project Charter

Stakeholder Registry

Communication Plan

Customized Scoring Criteria

Data Collection Templates

### Success Criteria

Executive sponsor approval of project charter

All key stakeholders identified and scheduled

Assessment criteria aligned with strategic objectives

## Phase 2: Data Collection & Inventory

### Duration: Week 2-4

### Objectives

Build comprehensive application inventory

Collect quantitative data on all applications

Validate data accuracy with application owners

Establish baseline metrics

### Activities

| Activity | Owner | Duration | Deliverable |
| --- | --- | --- | --- |
| Distribute data collection templates to IT teams | Analyst | Day 1 | Template distribution |
| Collect application inventory data | Analyst | Days 1-10 | Raw inventory data |
| Gather cost data (licensing, infrastructure, support) | Analyst | Days 3-10 | Cost inventory |
| Extract technical metrics (usage, performance, integrations) | Technical Lead | Days 5-12 | Technical metrics |
| Compile vendor/contract information | Analyst | Days 5-10 | Vendor registry |
| Data validation and cleansing | Analyst | Days 10-14 | Validated dataset |
| Import data into Rationalization Tool | Technical Lead | Day 14 | Loaded tool |
| Generate initial portfolio snapshot | Technical Lead | Day 14 | Baseline report |

### Data Points to Collect

Core Application Data:

Application name and description

Business owner and IT owner

Department/business unit

User count (active users)

Deployment model (on-prem, cloud, SaaS, hybrid)

Financial Data:

Annual licensing costs

Infrastructure costs (hosting, storage)

Support and maintenance costs

Development/enhancement costs

Total Cost of Ownership (TCO)

Technical Data:

Technology stack (languages, frameworks, databases)

Age of application

Last major update

Integration points (upstream/downstream)

Vendor support status

Security vulnerabilities

Compliance requirements

Business Data:

Business criticality rating

Revenue impact

Regulatory requirements

Strategic alignment score

Redundancy with other applications

### Data Sources

CMDB/Asset Management Systems

Financial systems (cost allocation)

IT Service Management tools

Application Performance Monitoring

Contract management systems

Security scanning tools

Direct surveys to application owners

### Deliverables

Complete Application Inventory (CSV/Excel)

Cost Analysis Summary

Technical Metrics Report

Data Quality Assessment

Initial Portfolio Dashboard

### Success Criteria

95%+ application coverage

Cost data for all applications

Technical health metrics available

Data validated by application owners

## Phase 3: Stakeholder Interviews

### Duration: Week 3-5 (overlaps with Phase 2)

### Objectives

Capture qualitative insights from key stakeholders

Understand business context and pain points

Assess change readiness and political landscape

Identify hidden dependencies and tribal knowledge

### Activities

| Activity | Owner | Duration | Deliverable |
| --- | --- | --- | --- |
| Schedule interviews (30-60 min each) | Project Coordinator | Days 1-3 | Interview calendar |
| Prepare interview guides per stakeholder type | Analyst | Days 1-3 | Customized questionnaires |
| Conduct executive interviews | Project Lead | Days 4-12 | Executive insights |
| Conduct business owner interviews | Analyst | Days 4-14 | Business perspectives |
| Conduct IT/technical interviews | Technical Lead | Days 7-14 | Technical insights |
| Conduct end-user interviews | Analyst | Days 10-14 | User feedback |
| Enter responses into Stakeholder Assessment Tool | Analyst | Ongoing | Captured responses |
| Analyze interview results | Analyst | Days 14-17 | Interview analysis report |

### Interview Strategy

Executive Sponsors (2-3 interviews)

Strategic priorities and constraints

Budget considerations

Risk tolerance

Timeline expectations

Success metrics

Business Owners (5-10 interviews)

Business value and criticality

Future needs and gaps

Pain points and frustrations

Change readiness

Dependencies on other systems

IT Leaders (3-5 interviews)

Technical health and sustainability

Support burden

Integration complexity

Security and compliance concerns

Modernization opportunities

Power Users (5-10 interviews)

Daily usage patterns

Satisfaction and usability

Workarounds and manual processes

Feature gaps

Training and support quality

### Interview Categories (from Stakeholder Assessment Tool)

**Business Value & Criticality** - Strategic importance, revenue impact

**User Satisfaction & Experience** - Usability, reliability, support quality

**Technical Health & Sustainability** - Integration, data quality, mobile access

**Change Readiness & Migration Potential** - Openness to change, training effort

**Dependencies & Integration** - Upstream/downstream systems, manual bridges

**Cost & Resource Awareness** - Value perception, support burden, duplicates

**Future Needs & Strategic Alignment** - Capability gaps, digital transformation fit

### Deliverables

Completed Interview Assessments (in tool)

Stakeholder Sentiment Analysis

Key Themes and Patterns Report

Risk and Opportunity Register

Verbatim Quotes Document

### Success Criteria

Minimum 15-20 interviews completed

All critical applications covered

Executive, business, and technical perspectives captured

Clear patterns and themes identified

## Phase 4: Assessment & Analysis

### Duration: Week 5-7

### Objectives

Calculate composite scores for all applications

Apply TIME framework categorization

Identify patterns, clusters, and anomalies

Generate compliance and risk assessments

Develop data-driven insights

### Activities

| Activity | Owner | Duration | Deliverable |
| --- | --- | --- | --- |
| Run scoring engine on portfolio | Technical Lead | Day 1 | Composite scores |
| Apply TIME framework categorization | Technical Lead | Day 1 | TIME quadrant placement |
| Run ML clustering analysis | Technical Lead | Day 2 | Application clusters |
| Identify anomalies and outliers | Analyst | Days 2-3 | Anomaly report |
| Conduct compliance assessment | Analyst | Days 3-5 | Compliance scores |
| Perform risk assessment | Analyst | Days 4-6 | Risk matrix |
| Analyze dependencies and integration map | Technical Lead | Days 5-7 | Dependency visualization |
| Correlate stakeholder scores with technical data | Analyst | Days 6-8 | Correlation analysis |
| Identify consolidation opportunities | Analyst | Days 7-9 | Consolidation candidates |
| Generate smart recommendations | Technical Lead | Day 9 | Recommendations list |
| What-if scenario modeling | Analyst | Days 9-10 | Scenario analysis |

### Analysis Techniques

Quantitative Analysis:

Composite scoring (weighted multi-criteria)

TIME framework (Tolerate/Invest/Migrate/Eliminate)

Total Cost of Ownership calculations

Usage vs. cost efficiency analysis

Technical debt assessment

Redundancy identification

Qualitative Analysis:

Stakeholder sentiment aggregation

Pain point frequency analysis

Change readiness heat mapping

Dependency complexity scoring

Strategic alignment assessment

Advanced Analytics:

ML clustering for natural application groupings

Anomaly detection for outliers

Predictive modeling for future state

Scenario comparison modeling

### TIME Framework Definitions

| Quadrant | Business Value | Technical Quality | Action |
| --- | --- | --- | --- |
| **Invest** | High | High | Enhance and grow |
| **Tolerate** | High | Low | Plan modernization |
| **Migrate** | Low | High | Consolidate or replace |
| **Eliminate** | Low | Low | Retire or decommission |

### Deliverables

Portfolio Scoring Summary

TIME Framework Visualization

Risk Assessment Report

Compliance Gap Analysis

Dependency Map

Consolidation Opportunities Report

ML Insights Report

What-If Scenario Results

### Success Criteria

All applications scored and categorized

Clear separation into rationalization categories

Risks quantified and prioritized

Quick wins identified

Dependencies mapped and understood

## Phase 5: Recommendations Development

### Duration: Week 7-9

### Objectives

Develop specific recommendations for each application

Quantify benefits (cost savings, risk reduction)

Define implementation approach

Prioritize actions based on value and feasibility

Build business cases for key initiatives

### Activities

| Activity | Owner | Duration | Deliverable |
| --- | --- | --- | --- |
| Develop recommendations per application | Analyst | Days 1-5 | Recommendation register |
| Estimate cost savings per recommendation | Analyst | Days 3-7 | Cost savings model |
| Assess implementation complexity | Technical Lead | Days 4-7 | Complexity ratings |
| Calculate ROI for major initiatives | Analyst | Days 6-9 | Business cases |
| Prioritize recommendations (value vs. effort) | Project Lead | Days 8-10 | Prioritized list |
| Validate recommendations with client SMEs | Project Lead | Days 10-12 | Validated recommendations |
| Refine based on feedback | Analyst | Days 12-14 | Final recommendations |

### Recommendation Categories

Retire/Eliminate:

Applications with low value and high cost

Redundant systems with better alternatives

End-of-life or unsupported systems

Unused or underutilized applications

Consolidate:

Overlapping functionality across multiple apps

Multiple instances of same application

Department-specific tools that could be enterprise-wide

Point solutions that could join platforms

Migrate/Modernize:

Legacy systems with high business value

On-prem applications suited for cloud

Monolithic apps to microservices

Outdated technology stacks

Invest/Enhance:

Strategic applications needing new features

High-value systems requiring performance improvements

Applications central to digital transformation

Maintain/Tolerate:

Stable applications meeting current needs

Systems with planned future replacement

Applications with high switching costs

### Business Case Components

Current state costs (annual)

Future state costs (projected)

One-time implementation costs

Net savings over 3-5 years

Risk reduction benefits

Strategic alignment benefits

Implementation timeline

Dependencies and prerequisites

### Deliverables

Application Recommendation Register

Cost Savings Model

Business Cases for Top 10 Initiatives

Prioritization Matrix

Risk Mitigation Plan

Quick Wins List (90-day actions)

### Success Criteria

Recommendation for every application

Quantified savings for retire/consolidate candidates

Business cases for major initiatives

Client validation of recommendations

Clear prioritization criteria

## Phase 6: Roadmap & Prioritization

### Duration: Week 9-10

### Objectives

Develop phased implementation roadmap

Sequence initiatives based on dependencies

Balance quick wins with strategic initiatives

Align with budget cycles and resource availability

Define governance and tracking mechanisms

### Activities

| Activity | Owner | Duration | Deliverable |
| --- | --- | --- | --- |
| Define roadmap horizons (30/60/90 day, 1yr, 3yr) | Project Lead | Day 1 | Horizon framework |
| Identify dependencies between initiatives | Technical Lead | Days 1-3 | Dependency map |
| Sequence initiatives | Project Lead | Days 3-5 | Sequenced roadmap |
| Resource and budget alignment | Analyst | Days 4-6 | Resource plan |
| Risk and contingency planning | Analyst | Days 5-7 | Risk mitigation plan |
| Define success metrics and KPIs | Project Lead | Days 6-8 | KPI dashboard design |
| Build governance model | Project Lead | Days 7-9 | Governance framework |
| Create detailed 90-day action plan | Analyst | Days 8-10 | 90-day plan |

### Roadmap Horizons

Immediate (0-90 Days):

Quick wins requiring minimal effort

Low-risk retirements

License true-ups and contract renegotiations

Documentation and process improvements

Short-term (3-12 Months):

Application retirements (complex)

Initial consolidations

Cloud migrations (lift-and-shift)

Vendor negotiations

Medium-term (1-2 Years):

Major consolidation projects

Platform modernization

Re-architecture initiatives

Strategic vendor decisions

Long-term (2-3 Years):

Full modernization programs

Digital transformation initiatives

Target architecture realization

### Prioritization Framework

Value Score (40%):

Cost savings potential

Risk reduction

Strategic alignment

User satisfaction improvement

Feasibility Score (30%):

Technical complexity

Resource availability

Vendor/contract constraints

Change management effort

Urgency Score (30%):

End-of-support deadlines

Security vulnerabilities

Compliance requirements

Business criticality

### Deliverables

Multi-Horizon Roadmap

90-Day Action Plan (detailed)

Resource Requirements

Budget Allocation

Governance Framework

KPIs and Success Metrics

Risk Register with Mitigations

### Success Criteria

Realistic and achievable timelines

Dependencies properly sequenced

Resources identified for Year 1

Executive buy-in on priorities

Clear ownership for each initiative

## Phase 7: Final Deliverables & Handoff

### Duration: Week 10-12

### Objectives

Compile comprehensive final report

Present findings to executive leadership

Transfer knowledge to client team

Establish ongoing governance

Plan for continuous improvement

### Activities

| Activity | Owner | Duration | Deliverable |
| --- | --- | --- | --- |
| Compile final report | Project Lead | Days 1-5 | Final report |
| Create executive presentation | Project Lead | Days 3-7 | Executive deck |
| Generate detailed appendices | Analyst | Days 5-8 | Supporting materials |
| Prepare tool handover documentation | Technical Lead | Days 6-9 | User guides |
| Executive presentation rehearsal | Project Lead | Day 9 | Refined presentation |
| Final executive presentation | Project Lead | Day 10 | Presented findings |
| Knowledge transfer sessions | All | Days 10-12 | Trained client team |
| Project closeout and retrospective | Project Lead | Day 12 | Lessons learned |

### Final Report Structure

Executive Summary (2-3 pages)

Key findings and insights

Total savings opportunity

Top recommendations

Critical risks

Recommended next steps

Portfolio Assessment (10-15 pages)

Portfolio overview and demographics

Scoring methodology and results

TIME framework analysis

Compliance and risk assessment

Cost analysis

Stakeholder Insights (5-10 pages)

Interview summary

Key themes and patterns

Sentiment analysis

Change readiness assessment

Recommendations (15-20 pages)

Detailed recommendations by category

Business cases for major initiatives

Prioritization rationale

Dependencies and constraints

Implementation Roadmap (5-10 pages)

Multi-horizon roadmap

90-day action plan

Resource requirements

Governance model

KPIs and tracking

Appendices

Complete application inventory

Individual application scorecards

Interview transcripts/summaries

Cost models and calculations

Risk register

### Executive Presentation Agenda

Project overview and approach (5 min)

Key findings - portfolio health (10 min)

Stakeholder insights (10 min)

Top recommendations (15 min)

Savings opportunity (10 min)

Roadmap overview (10 min)

Next steps and governance (10 min)

Q&A (20 min)

### Knowledge Transfer Topics

Tool usage and administration

Scoring model customization

Running assessments

Generating reports

Maintaining data currency

Ongoing stakeholder interviews

### Deliverables

Final Report (Word/PDF)

Executive Presentation (PowerPoint)

Application Scorecards

Tool Access and Training

User Documentation

Data Exports

Lessons Learned Document

### Success Criteria

Executive presentation accepted

Recommendations approved for action

Budget allocated for Year 1

Governance structure established

Client team trained on tools

Project formally closed

## Project Resources

### Team Structure

| Role | Responsibilities | Allocation |
| --- | --- | --- |
| **Executive Sponsor** | Strategic direction, issue escalation, final approvals | 5% |
| **Project Lead** | Overall delivery, stakeholder management, recommendations | 80-100% |
| **Technical Lead** | Tool configuration, data analysis, technical assessment | 60-80% |
| **Business Analyst** | Data collection, interviews, documentation | 100% |
| **Project Coordinator** | Scheduling, logistics, status reporting | 25-50% |

### Client Resources Required

Executive sponsor (decision authority)

IT leadership (2-3 people)

Business leadership (2-3 people)

Application owners (as needed for interviews/validation)

Data providers (CMDB, finance, contracts)

## Risk Management

### Common Risks

| Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| Incomplete data | High | Medium | Early data validation, multiple sources |
| Stakeholder availability | Medium | High | Early scheduling, executive mandate |
| Scope creep | Medium | Medium | Clear charter, change control process |
| Political resistance | High | Medium | Executive sponsorship, transparent process |
| Data quality issues | Medium | High | Validation checkpoints, owner sign-off |
| Unrealistic expectations | High | Medium | Clear communication, regular updates |

## Success Metrics

### Project Success

On-time delivery (within 2 weeks of target)

On-budget completion (within 10% variance)

Client satisfaction score (8+ out of 10)

All deliverables accepted

### Business Outcomes (Post-Implementation)

Cost savings achieved vs. projected (target: 80%+)

Applications retired within Year 1 (target: 50%+ of identified)

Risk reduction (measured by audit findings)

User satisfaction improvement (post-implementation survey)

## Tools & Templates

### Application Rationalization Tool Features Used

Data upload and validation

Composite scoring engine

TIME framework visualization

Stakeholder assessment interviews

Compliance assessment

Risk assessment

ML insights and clustering

What-if scenario analysis

Smart recommendations

Report generation (PDF, PowerPoint)

### Supporting Templates

Data collection spreadsheet

Stakeholder interview guide

Business case template

Executive presentation template

Final report template

## Appendix: Sample Timeline

### 8-Week Engagement (Small Portfolio: <100 apps)

| Week | Phase | Key Activities |
| --- | --- | --- |
| 1 | Initiation | Kick-off, stakeholder ID, tool setup |
| 2 | Data Collection | Inventory, costs, technical data |
| 3 | Data + Interviews | Data validation, begin interviews |
| 4 | Interviews | Complete interviews, enter data |
| 5 | Analysis | Scoring, TIME, risk, compliance |
| 6 | Recommendations | Develop recs, business cases |
| 7 | Roadmap | Prioritization, sequencing |
| 8 | Delivery | Final report, presentation, handoff |

### 12-Week Engagement (Large Portfolio: 300+ apps)

| Week | Phase | Key Activities |
| --- | --- | --- |
| 1-2 | Initiation | Kick-off, stakeholder ID, tool setup, criteria |
| 2-4 | Data Collection | Phased data collection across business units |
| 3-6 | Interviews | 30+ interviews across all stakeholder types |
| 5-7 | Analysis | Comprehensive analysis, advanced analytics |
| 7-9 | Recommendations | Detailed recs, multiple business cases |
| 9-11 | Roadmap | Multi-horizon roadmap, detailed Year 1 plan |
| 11-12 | Delivery | Comprehensive report, exec presentation, training |

*This project plan template should be customized based on client size, complexity, and specific objectives.*