## Project Overview
APPLICATION RATIONALIZATION PROJECT PLAN
Project Information
Client Name: | [Enter Client Name] |  | Project Manager: | [Enter PM Name]
Project Start Date: | [Enter Date] |  | Technical Lead: | [Enter TL Name]
Target End Date: | [Enter Date] |  | Business Analyst: | [Enter BA Name]
Portfolio Size: | [# of Applications] |  | Executive Sponsor: | [Enter Sponsor]
Project Objectives
1. | Evaluate application portfolio for rationalization opportunities
2. | Identify cost savings and risk reduction opportunities
3. | Develop prioritized implementation roadmap
4. | Build business cases for top initiatives
Success Criteria
1. | Complete inventory of all applications with scores
2. | Minimum 20 stakeholder interviews completed
3. | Quantified savings opportunity identified
4. | Executive-approved implementation roadmap
Timeline Summary
Phase | Duration | Start | End | Status
1. Initiation & Discovery | 2 weeks |  |  | Not Started
2. Data Collection & Inventory | 3 weeks |  |  | Not Started
3. Stakeholder Interviews | 3 weeks |  |  | Not Started
4. Assessment & Analysis | 2 weeks |  |  | Not Started
5. Recommendations Development | 2 weeks |  |  | Not Started
6. Roadmap & Prioritization | 1.5 weeks |  |  | Not Started
7. Final Deliverables & Handoff | 1.5 weeks |  |  | Not Started

## Detailed Tasks
ID | Phase | Task | Owner | Start Date | End Date | Duration (Days) | Status | % Complete | Dependencies | Notes
1.1 | 1. Initiation | Conduct project kick-off meeting | Project Lead |  |  | 1 | Not Started | 0 |  | Include exec sponsor
1.2 | 1. Initiation | Review and sign project charter | Exec Sponsor |  |  | 2 | Not Started | 0 | 1.1
1.3 | 1. Initiation | Identify key stakeholders | Project Lead |  |  | 3 | Not Started | 0 | 1.1 | Min 20 stakeholders
1.4 | 1. Initiation | Review existing documentation | Analyst |  |  | 5 | Not Started | 0 | 1.1 | Architecture, contracts
1.5 | 1. Initiation | Define scoring criteria with client | Project Lead |  |  | 2 | Not Started | 0 | 1.3
1.6 | 1. Initiation | Configure assessment tool | Technical Lead |  |  | 3 | Not Started | 0 | 1.5
1.7 | 1. Initiation | Create data collection templates | Analyst |  |  | 2 | Not Started | 0 | 1.5
1.8 | 1. Initiation | Establish communication plan | Project Lead |  |  | 1 | Not Started | 0 | 1.2
2.1 | 2. Data Collection | Distribute data templates to IT teams | Analyst |  |  | 1 | Not Started | 0 | 1.7
2.2 | 2. Data Collection | Collect application inventory data | Analyst |  |  | 10 | Not Started | 0 | 2.1
2.3 | 2. Data Collection | Gather cost data (licensing, infra) | Analyst |  |  | 7 | Not Started | 0 | 2.1
2.4 | 2. Data Collection | Extract technical metrics | Technical Lead |  |  | 7 | Not Started | 0 | 2.1
2.5 | 2. Data Collection | Compile vendor/contract info | Analyst |  |  | 5 | Not Started | 0 | 2.1
2.6 | 2. Data Collection | Validate data with app owners | Analyst |  |  | 4 | Not Started | 0 | 2.2-2.4
2.7 | 2. Data Collection | Clean and normalize data | Analyst |  |  | 3 | Not Started | 0 | 2.6
2.8 | 2. Data Collection | Import data into tool | Technical Lead |  |  | 1 | Not Started | 0 | 2.7
3.1 | 3. Interviews | Schedule all stakeholder interviews | Coordinator |  |  | 3 | Not Started | 0 | 1.3
3.2 | 3. Interviews | Prepare interview guides | Analyst |  |  | 2 | Not Started | 0 | 1.6
3.3 | 3. Interviews | Conduct executive interviews | Project Lead |  |  | 5 | Not Started | 0 | 3.1
3.4 | 3. Interviews | Conduct business owner interviews | Analyst |  |  | 8 | Not Started | 0 | 3.1
3.5 | 3. Interviews | Conduct IT/technical interviews | Technical Lead |  |  | 5 | Not Started | 0 | 3.1
3.6 | 3. Interviews | Enter responses into tool | Analyst |  |  | 3 | Not Started | 0 | 3.3-3.5
3.7 | 3. Interviews | Analyze interview results | Analyst |  |  | 3 | Not Started | 0 | 3.6
4.1 | 4. Analysis | Run scoring engine | Technical Lead |  |  | 1 | Not Started | 0 | 2.8
4.2 | 4. Analysis | Apply TIME framework | Technical Lead |  |  | 1 | Not Started | 0 | 4.1
4.3 | 4. Analysis | Run ML clustering | Technical Lead |  |  | 1 | Not Started | 0 | 4.1
4.4 | 4. Analysis | Conduct compliance assessment | Analyst |  |  | 3 | Not Started | 0 | 4.1
4.5 | 4. Analysis | Perform risk assessment | Analyst |  |  | 3 | Not Started | 0 | 4.1
4.6 | 4. Analysis | Map dependencies | Technical Lead |  |  | 3 | Not Started | 0 | 2.8
4.7 | 4. Analysis | Generate recommendations | Technical Lead |  |  | 1 | Not Started | 0 | 4.1-4.6
5.1 | 5. Recommendations | Develop per-app recommendations | Analyst |  |  | 5 | Not Started | 0 | 4.7
5.2 | 5. Recommendations | Estimate cost savings | Analyst |  |  | 4 | Not Started | 0 | 5.1
5.3 | 5. Recommendations | Assess complexity | Technical Lead |  |  | 3 | Not Started | 0 | 5.1
5.4 | 5. Recommendations | Build business cases | Project Lead |  |  | 4 | Not Started | 0 | 5.2
5.5 | 5. Recommendations | Prioritize recommendations | Project Lead |  |  | 2 | Not Started | 0 | 5.1-5.3
5.6 | 5. Recommendations | Validate with client | Project Lead |  |  | 3 | Not Started | 0 | 5.5
6.1 | 6. Roadmap | Define roadmap horizons | Project Lead |  |  | 1 | Not Started | 0 | 5.6
6.2 | 6. Roadmap | Sequence initiatives | Project Lead |  |  | 2 | Not Started | 0 | 6.1
6.3 | 6. Roadmap | Align resources/budget | Analyst |  |  | 2 | Not Started | 0 | 6.2
6.4 | 6. Roadmap | Define KPIs | Project Lead |  |  | 2 | Not Started | 0 | 6.2
6.5 | 6. Roadmap | Create 90-day plan | Analyst |  |  | 2 | Not Started | 0 | 6.2
7.1 | 7. Deliverables | Compile final report | Project Lead |  |  | 5 | Not Started | 0 | 6.5
7.2 | 7. Deliverables | Create exec presentation | Project Lead |  |  | 4 | Not Started | 0 | 7.1
7.3 | 7. Deliverables | Prepare tool handover | Technical Lead |  |  | 3 | Not Started | 0 | 7.1
7.4 | 7. Deliverables | Final presentation | Project Lead |  |  | 1 | Not Started | 0 | 7.2
7.5 | 7. Deliverables | Knowledge transfer | All |  |  | 2 | Not Started | 0 | 7.4
7.6 | 7. Deliverables | Project closeout | Project Lead |  |  | 1 | Not Started | 0 | 7.5

## Stakeholder Registry
ID | Name | Title/Role | Department | Email | Phone | Stakeholder Type | Influence Level | Interview Date | Interview Status | Applications | Notes

## Deliverables Tracker
Phase | Deliverable | Owner | Due Date | Status | Approved By | Location
1. Initiation | Project Charter | Project Lead |  | Not Started
1. Initiation | Stakeholder Registry | Project Lead |  | Not Started
1. Initiation | Data Collection Templates | Analyst |  | Not Started
2. Data Collection | Application Inventory (CSV) | Analyst |  | Not Started
2. Data Collection | Cost Analysis Summary | Analyst |  | Not Started
3. Interviews | Completed Assessments | Analyst |  | Not Started
3. Interviews | Stakeholder Analysis Report | Analyst |  | Not Started
4. Analysis | Portfolio Scoring Summary | Technical Lead |  | Not Started
4. Analysis | TIME Framework Analysis | Technical Lead |  | Not Started
4. Analysis | Risk Assessment Report | Analyst |  | Not Started
5. Recommendations | Recommendation Register | Analyst |  | Not Started
5. Recommendations | Business Cases | Project Lead |  | Not Started
6. Roadmap | Implementation Roadmap | Project Lead |  | Not Started
6. Roadmap | 90-Day Action Plan | Analyst |  | Not Started
7. Deliverables | Final Report | Project Lead |  | Not Started
7. Deliverables | Executive Presentation | Project Lead |  | Not Started

## Risk Register
ID | Risk Description | Probability | Impact | Mitigation | Owner | Status
R001 | Incomplete application data | Medium | High | Multiple sources, validation | Analyst | Open
R002 | Stakeholder availability | High | Medium | Early scheduling, exec mandate | Coordinator | Open
R003 | Scope creep | Medium | Medium | Change control process | Project Lead | Open
R004 | Political resistance | Medium | High | Exec sponsorship | Project Lead | Open
R005 | Data quality issues | High | Medium | Validation checkpoints | Analyst | Open